## Timelines
| 2015-07-15 |  |  |  | 0 = completed 1 = in progress
Phase | Tasks | Start Date | Duration | End Date | Remaining days | OPI
| ***Project started at end of January 2014 with the first several months not reflected in this project plan. January to May = ANALYZE & DESIGN for all 4 Phases at a high level. May to August = DEVELOP for Phase 1. Future steps in ADDIE may see a short return to further expand on DESIGN for each Phase as we near time to Develop pre-pilot (Implementation). |  |  |  |  | July and August 1
DEVELOP 1 | Alpha Testing 1.0 | 2014-07-21 | 5 | 2014-07-25 | 0 | Sandra / Cara / Yvonna
1 | Coding of content (English) | 2014-07-25 | 65 | 2014-08-20 | 0 | Roger / John / Fred
1 | Send content for editing | 2014-08-01 | 14 | 2014-08-14 | 0 | Tatiana / Designers to submit to her
August 4-8
1 | Review editing from Translation Bureau | 2014-08-07 | 7 | 2014-08-15 | 0 | Designers (24 hours each)
1 | Content review (EX, Senior EX & regions) | 2014-08-08 | 4 | 2014-08-12 | 0 | Cara liaises with reviewers / Designers have 72 hours to review/adjust
August 11-15
1 | Send invitations for Alpha testing 2.0 | 2014-08-11 | 2 | 2014-08-12 | 0 | Sandra (check with NLJ / NMC)
1 | Send content for translation & wait for completion | 2014-08-11 | 4 | 2014-09-04 | -225 | Tatiana / Designers to submit to her
DEVELOP 2 | Build Phase 2 fictional org chart | 2014-08-12 | 35 | 2014-09-09 | -222 | Designers
1 | Finalize Alpha testing 2.0 questions | 2014-08-14 | 1 | 2014-08-14 | 0 | Sandra / Cara / Validate with ALL
August 18-22
1 | Final English phase 1 content submitted (after editing & reviews) | 2014-08-18 | 2 | 2014-08-22 | -234 | Designers drop docs in GCDocs
2 | Phase 2 high level draft comparison | 2014-09-18 | 14 | 2014-09-02 | -227 | ALL
1 | Alpha Testing 2.0 | 2014-08-19 | 4 | 2014-08-22 | -234 | Sandra / Cara / ALL to assist
2 | Designers draft Phase 2 content & facilitator's notes (with weekly check-in points) | 2014-08-20 | 35 | 2014-09-29 | -208 | Designers
1 | Decisions on results of Alpha Testing 2.0 | 2014-08-22 | 2 | 2014-08-25 | -233 | Sandra / Cara / ALL
1 | Final decision required on registration process for Phase 1 pilot participants (then prep Comms accordingly) ** RISK - of eSchool functions not being ready. May have to do this manually | 2014-08-22 | 6 | 2014-08-28 | -230 | eSchool? NLJ? JJJ?
August 25-29
1 | Recruitment - requires Comms for written pieces & translation - link with NMC | 2014-08-25 | 17 | 2014-09-09 | -222 | Jean Cardinal (Client Relations) to liaise with NMC
1 | Review French translation | 2014-08-29 | 6 | 2014-09-04 | -225 | Designers (48 hours each)
September 1-5
1 | French content loaded into Moodle | 2014-09-02 | 12 | 2014-09-14 | -218 | Roger / John / Fred
1 | Write welcome instructions & send to translation | 2014-09-02 | 7 | 2014-09-09 | -222 | Implementation team with Comms
1 | Identify discussion forum SMEs | 2014-09-02 | 7 | 2014-09-08 | -223 | Implementation team to coordinate
September 8-12
1 | Discussion forum SMEs review Phase 1 material in prep | 2014-09-09 | 20 | 2014-09-29 | -208 | Implementation team to coordinate
September 15-19
1 | IT freezes Moodle | 2014-09-15 | 14 | 2014-09-29 | -208 | Elie & IT
1 | Welcome instructions sent to pilot participants? (requires translation 1st) | 2014-09-15 | 1 | 2014-09-15 | -218 | Implementation team
September 29 - October 3
2 | Deadline for Phase 2 ENG content (for review) | 2014-09-29 | 1 | 2014-09-29 | -208 | Designers
IMPLEMENT 1 | PHASE 1 PILOT Send link to enter program Implementation team monitors discussion forum & flags to design team to respond OR to flag to SMEs Who handles questions on access issues - CCC or Implementation team? | 2014-09-30 | 30 | 2014-10-30 | -185 | Implementation team & Design team
EVALUATE 1 | Begin review of live evaluations **RISK - have to make changes based on whatever feedback is in before end of pilot phase. May not have many global L1s to use. Can't go much beyond this date b/c no time to make changes/translate/input before launch | 2014-09-30 | 31 | 2014-10-31 | -184 | Cara's team / Designers
DESIGN & DEVELOP 3 | Content design: concept & weekly check-in meetings | 2014-09-30 | 49 | 2014-12-19 | -149 | Designers
2 | Content review (Executive Advisor, regional manager) | 2014-09-30 | 3 | 2014-10-02 | -205 | Cara liaises with reviewers
2 | Input changes from content review | 2014-10-03 | 5 | 2014-10-08 | -201 | Cara liaises with reviewers / Designers
October 6-10
2 | Final checking of English formatting before sending to translation | 2014-10-09 | 2 | 2014-10-13 | -198 | Implementation team Graphic design required?? Is there a logo for the program?
October 13-17
2 | Content translation | 2014-10-14 | 21 | 2014-11-04 | -182 | Tatiana / Designers to submit to her
1 | Changes from Beta Phase 1 by designers & send to translation as soon as pieces are ready (pay for priority) **RISK - translation not coming back in time if heavy re-working of material | 2014-10-15 | 16 | 2014-11-01 | -183 | Designers
October 20-24
1 | Edesigners input changes into Moodle (ENG first then pieces coming back from translation near deadline) | 2014-10-20 | 18 | 2014-11-07 | -179 | Roger / John / Fred
2 | Facilitator prep | 2014-10-24 | 30 | 2014-11-21 | -169 | Implementation team to coordinate with Facilitators How to coordinate with designers?
November 3-7
2 | Review French translation | 2014-11-05 | 5 | 2014-11-10 | -178 | Designers have 48 hours
1 | IT freezes system?? NEED TO CONFIRM WITH school / IT | 2014-11-07 | 21 | 2014-11-27 | #REF! | eSchool IT
1 | Phase 1 Pilot Report | 2014-11-07 | 14 | 2014-12-14 | -153 | Design & implementation team
November 10-14
2 | Final checking of French formatting before printing | 2014-11-10 | 2 | 2014-11-12 | -176 | Implementation team
2 | Print material for NCR and send docs to regions to print | 2014-11-13 | 7 | 2014-11-20 | -170 | Implementation team
November 24-28
IMPLEMENT 2 | PHASE 2 PILOT NCR, Halifax, Edmonton, Montréal Schedule offering nearer beginning of this time period if possible | 2014-11-24 | 21 | 2014-12-12 | -154 | Implementation team
1 | PHASE 1 OFFICIAL LAUNCH | 2014-11-28 | 1 | 2014-11-28 | -164 | eSchool IT & implementation team
January 5-9
3 | Send content for translation & wait for completion | 2015-01-06 | 4 | 2015-02-13 | -109 | Tatiana / Designers to submit to her
3 | Final English phase 1 content submitted (after editing & reviews) | 2015-01-06 | 1 | 2015-01-06 | -137 | Designers drop docs in GCDocs
2 | Deadline for Phase 2 revisions | 2015-01-09 | 1 | 2015-01-09 | -134 | Designers
2 | Content translation of changes | 2015-01-09 | 10 | 2015-01-19 | -128 | Tatiana / Designers to submit to her
2 | Phase 2 Pilot Report | 2015-01-09 | 14 | 2015-01-23 | #VALUE! | Design & implementation team
2 | Facilitator prep | 2015-01-09 | 30 | 2015-02-06 | -114 | Implementation team to coordinate with Facilitators How to coordinate with designers?
January 19-23
3 | Deadline for Phase 3 ENG content (for review) | 2015-01-19 | 30 | 2015-02-13 | 30035 | Designers
3 | Content review (EX, Senior EX & regions) | 2015-01-19 | 20 | 2015-02-17 | #VALUE! | Cara liaises with reviewers
2 | Review French translation | 2015-01-19 | 3 | 2015-01-21 | -126 | Designers have 48 hours
3 | Review French translation | 2015-01-21 | 2 | 2015-02-19 | -105 | Designers (48 hours each)
2 | Final checking of French formatting before printing | 2015-01-22 | 2 | 2015-01-23 | -124 | Implementation team
2 | French content loaded into Moodle | 2015-01-23 | 12 | 2015-02-23 | -103 | Roger / Fred
January 26-30
2 | Print material for NCR and send docs to regions to print | 2015-01-26 | 7 | 2015-02-02 | -118 | Implementation team
February 9-13
2 | PHASE 2 OFFICIAL LAUNCH | 2015-02-09 | 1 | 2015-02-09 | -113 | Implementation team
February 23-27
IMPLEMENT 3 | PHASE 3 PILOT | 2015-02-23 | 30 | 2015-04-02 | #VALUE! | Implementation team
4 | Designers draft Phase 4 content & facilitator's notes (with weekly check-in points) | 2015-02-23 | 30 | 2015-03-23 | #VALUE! | Designers
March 9-13
EVALUATE 3 | Begin review of live evaluations **RISK - have to make changes based on whatever feedback is in before end of pilot phase. May not have many global L1s to use. Can't go much beyond this date b/c no time to make changes/translate/input before launch | 2015-03-13 | 37 | 2015-04-06 |  | Cara's team / Designers
March 16-20
3 | Changes from Beta Phase 3 by designers & send to translation as soon as pieces are ready (pay for priority) **RISK - translation not coming back in time if heavy re-working of material | 2015-03-16 | 28 | 2015-04-17 |  | Designers
March 23-27
4 | Deadline for Phase 4 ENG content (for review) | 2015-03-23 | 1 | 2015-03-23 |  | Designers
4 | Content review (Executive Advisor, regional manager) | 2015-03-23 | 3 | 2015-03-26 |  | Cara liaises with reviewers
4 | Input changes from content review | 2015-03-26 | 4 | 2015-03-30 |  | Cara liaises with reviewers / Designers
March 30 - April 3
4 | Final checking of English formatting before sending to translation | 2015-03-31 | 2 | 2015-04-02 | -75 | Implementation team Graphic design required?? Is there a logo for the program?
4 | Content translation | 2015-04-03 | 14 | 2015-04-17 | -64 | Tatiana / Designers to submit to her
April 6-10
4 | Facilitator prep | 2015-04-07 | 30 | 2015-05-08 | -49 | Implementation team to coordinate with Facilitators How to coordinate with designers?
3 | Phase 3 content changes ready (send to translation) | 2015-04-09 | 1 | 2015-04-09 | -70 | Tatiana
April 20-24
IMPLEMENT 4 | Review French translation | 2015-04-20 | 5 | 2015-04-24 | -59 | Designers have 48 hours
3 | Phase 3 Pilot Report | 2015-04-22 | 2 | 2015-05-01 | #REF! | Design & implementation team
3 | Review translation as it comes back in | 2015-04-22 | 2 | 2015-04-23 | -60 | Designers
3 | Edesigners input changes into Moodle (Whatever is ready first then pieces coming back from translation near deadline) | 2015-04-24 | 12 | 2015-05-06 | -51 | Roger / John / Fred
April 27 - May 1
4 | Final checking of French formatting before printing | 2015-04-27 | 2 | 2015-04-28 | -57 | Implementation team
4 | Print material for NCR and send docs to regions to print | 2015-04-29 | 7 | 2015-05-06 | -51 | Implementation team
May 11-15
4 | PHASE 3 OFFICIAL LAUNCH | 2015-05-11 | 1 | 2015-05-11 | -48 | Implementation team
EVALUATE 4 | PHASE 4 PILOT | 2015-05-11 | 21 | 2015-05-29 | -34 | Implementation team
June 1-5
4 | Designers review evaluations/observations & revise Phase 4 | 2015-06-01 | 18 | 2015-06-18 | -20 | Designers
June 15-19
4 | Deadline for Phase 4 revisions | 2015-06-18 | 1 | 2015-06-18 | -20 | Designers
4 | Content translation of changes | 2015-06-19 | 7 | 2015-06-26 | #REF! | Tatiana / Designers to submit to her
4 | Phase 4 Pilot Report | 2015-06-19 | 14 | 2015-07-03 | -9 | Tatiana / Designers to submit to her
June 29 - July 3
4 | Facilitator prep | 2015-06-29 | 21 | 2015-07-17 | 3 | Implementation team to coordinate with Facilitators How to coordinate with designers?
4 | Review French translation | 2015-06-29 | 3 | 2015-07-02 | -10 | Designers have 48 hours
4 | Final checking of French formatting before printing | 2015-07-03 | 4 | 2015-07-07 | -7 | Implementation team
July 6-10
4 | Print material for NCR and send docs to regions to print | 2015-07-08 | 7 | 2015-07-15 | 1 | Implementation team
July 20-24
4 | PHASE 4 OFFICIAL LAUNCH | 2015-07-20 | 1 | 2015-07-20 | 4 | Implementation team
Formulas:
Remaining days = NETWORKDAYS(B1,[End Date])
Remaining days = NETWORKDAYS(B1, [End Date])

## Sheet1
Phase | Tasks | Start Date | Duration | End Date | Remaining days | OPI
July and August 1
1 | Alpha Testing 1.0 | 2014-07-21 | 5 | 2014-07-25 | 0 | Sandra / Cara / Yvonna
1 | Coding of content (English) | 2014-07-25 | 65 | 2014-08-20 | 0 | Roger / John / Fred
1 | Send content for editing | 2014-08-01 | 14 | 2014-08-14 | 0 | Tatiana / Designers to submit to her
August 4-8
1 | Review editing from Translation Bureau | 2014-08-07 | 7 | 2014-08-15 | 0 | Designers (24 hours each)
1 | Content review (EX, Senior EX & regions) | 2014-08-08 | 4 | 2014-08-12 | 0 | Cara liaises with reviewers / Designers have 72 hours to review/adjust
August 11-15
1 | Send invitations for Alpha testing 2.0 | 2014-08-11 | 2 | 2014-08-12 | 0 | Sandra (check with NLJ / NMC)
1 | Send content for translation & wait for completion | 2014-08-11 | 4 | 2014-09-04 | #REF! | Tatiana / Designers to submit to her
2 | Build Phase 2 fictional org chart | 2014-08-12 | 35 | 2014-09-09 | #REF! | Designers
1 | Finalize Alpha testing 2.0 questions | 2014-08-14 | 1 | 2014-08-14 | 0 | Sandra / Cara / Validate with ALL
August 18-22
1 | Final English phase 1 content submitted (after editing & reviews) | 2014-08-18 | 2 | 2014-08-22 | #REF! | Designers drop docs in GCDocs
2 | Phase 2 high level draft comparison | 2014-09-18 | 14 | 2014-09-02 | #REF! | ALL
1 | Alpha Testing 2.0 | 2014-08-19 | 4 | 2014-08-22 | #REF! | Sandra / Cara / ALL to assist
2 | Designers draft Phase 2 content & facilitator's notes (with weekly check-in points) | 2014-08-20 | 35 | 2014-09-29 | #REF! | Designers
1 | Decisions on results of Alpha Testing 2.0 | 2014-08-22 | 2 | 2014-08-25 | #REF! | Sandra / Cara / ALL
1 | Final decision required on registration process for Phase 1 pilot participants (then prep Comms accordingly) ** RISK - of eSchool functions not being ready. May have to do this manually | 2014-08-22 | 6 | 2014-08-28 | #REF! | eSchool? NLJ? JJJ?
August 25-29
1 | Recruitment - requires Comms for written pieces & translation - link with NMC | 2014-08-25 | 17 | 2014-09-09 | #REF! | Jean Cardinal (Client Relations) to liaise with NMC
1 | Review French translation | 2014-08-29 | 6 | 2014-09-04 | #REF! | Designers (48 hours each)
September 1-5
1 | French content loaded into Moodle | 2014-09-02 | 12 | 2014-09-14 | #REF! | Roger / John / Fred
1 | Write welcome instructions & send to translation | 2014-09-02 | 7 | 2014-09-09 | #REF! | Implementation team with Comms
1 | Identify discussion forum SMEs | 2014-09-02 | 7 | 2014-09-08 | #REF! | Implementation team to coordinate
September 8-12
1 | Discussion forum SMEs review Phase 1 material in prep | 2014-09-09 | 20 | 2014-09-29 | #REF! | Implementation team to coordinate
September 15-19
1 | IT freezes Moodle | 2014-09-15 | 14 | 2014-09-29 | #REF! | Elie & IT
1 | Welcome instructions sent to pilot participants? (requires translation 1st) | 2014-09-15 | 1 | 2014-09-15 | #REF! | Implementation team
September 29 - October 3
2 | Deadline for Phase 2 ENG content (for review) | 2014-09-29 | 1 | 2014-09-29 | #REF! | Designers
1 | PHASE 1 PILOT Send link to enter program PE monitors discussion forums and flags to SMEs? Who handles questions on access issues - CCC or Implementation team? | 2014-09-30 | 30 | 2014-10-30 | #REF! | Implementation team
1 | Begin review of live evaluations **RISK - have to make changes based on whatever feedback is in before end of pilot phase. May not have many global L1s to use. Can't go much beyond this date b/c no time to make changes/translate/input before launch | 2014-09-30 | 31 | 2014-10-31 | #REF! | Cara's team / Designers
3 | Content design: concept & weekly check-in meetings | 2014-09-30 | 49 | 2014-12-19 | #REF! | Designers
2 | Content review (Executive Advisor, regional manager) | 2014-09-30 | 3 | 2014-10-02 | #REF! | Cara liaises with reviewers
2 | Input changes from content review | 2014-10-03 | 5 | 2014-10-08 | #REF! | Cara liaises with reviewers / Designers
October 6-10
2 | Final checking of English formatting before sending to translation | 2014-10-09 | 2 | 2014-10-13 | #REF! | Implementation team Graphic design required?? Is there a logo for the program?
October 13-17
2 | Content translation | 2014-10-14 | 21 | 2014-11-04 | #REF! | Tatiana / Designers to submit to her
1 | Changes from Beta Phase 1 by designers & send to translation as soon as pieces are ready (pay for priority) **RISK - translation not coming back in time if heavy re-working of material | 2014-10-15 | 16 | 2014-11-01 | #REF! | Designers
October 20-24
1 | Edesigners input changes into Moodle (ENG first then pieces coming back from translation near deadline) | 2014-10-20 | 18 | 2014-11-07 | #REF! | Roger / John / Fred
2 | Facilitator prep | 2014-10-24 | 30 | 2014-11-21 | #REF! | Implementation team to coordinate with Facilitators How to coordinate with designers?
November 3-7
2 | Review French translation | 2014-11-05 | 5 | 2014-11-10 | #REF! | Designers have 48 hours
1 | IT freezes system?? NEED TO CONFIRM WITH school / IT | 2014-11-07 | 21 | 2014-11-27 | #REF! | eSchool IT
November 10-14
2 | Final checking of French formatting before printing | 2014-11-10 | 2 | 2014-11-12 | #REF! | Implementation team
2 | Print material for NCR and send docs to regions to print | 2014-11-13 | 7 | 2014-11-20 | #REF! | Implementation team
November 24-28
2 | PHASE 2 PILOT NCR, Halifax, Edmonton, Montréal Schedule offering nearer beginning of this time period if possible | 2014-11-24 | 21 | 2014-12-12 | #REF! | Implementation team
1 | PHASE 1 OFFICIAL LAUNCH | 2014-11-28 | 1 | 2014-11-28 | #REF! | eSchool IT & implementation team
December 15-19
2 | Designers review evaluations/observations & revise Phase 2 | 2014-12-15 | 28 | 2014-09-01 | #REF! | Designers
3 | Deadline for Phase 3 ENG content (for review) | 2014-12-19 | 1 | 2014-12-19 | #REF! | Designers
3 | Content review (EX, Senior EX & regions) | 2014-12-19 | 20 | 2015-01-06 | #REF! | Cara liaises with reviewers
December 29 - January 2
4 | Designers draft Phase 4 content & facilitator's notes (with weekly check-in points) | 2015-01-02 | 45 | 2015-03-16 | #REF! | Designers
January 5-9
3 | Send content for translation & wait for completion | 2015-01-06 | 4 | 2015-01-20 | #REF! | Tatiana / Designers to submit to her
3 | Final English phase 1 content submitted (after editing & reviews) | 2015-01-06 | 1 | 2015-01-06 | #REF! | Designers drop docs in GCDocs
2 | Deadline for Phase 2 revisions | 2015-01-09 | 1 | 2015-01-09 | #REF! | Designers
2 | Content translation of changes | 2015-01-09 | 10 | 2015-01-19 | #REF! | Tatiana / Designers to submit to her
2 | Facilitator prep | 2015-01-09 | 30 | 2015-02-06 | #REF! | Implementation team to coordinate with Facilitators How to coordinate with designers?
January 19-23
2 | Review French translation | 2015-01-19 | 3 | 2015-01-21 | #REF! | Designers have 48 hours
3 | Review French translation | 2015-01-21 | 2 | 2015-01-22 | #REF! | Designers (48 hours each)
2 | Final checking of French formatting before printing | 2015-01-22 | 2 | 2015-01-23 | #REF! | Implementation team
3 | French content loaded into Moodle | 2015-01-23 | 12 | 2015-02-04 | #REF! | Roger / John / Fred
January 26-30
2 | Print material for NCR and send docs to regions to print | 2015-01-26 | 7 | 2015-02-02 | #REF! | Implementation team
February 9-13
2 | PHASE 2 OFFICIAL LAUNCH | 2015-02-09 | 1 | 2015-02-09 | #REF! | Implementation team
3 | PHASE 3 PILOT | 2015-02-09 | 30 | 2015-03-06 | #REF! | Implementation team
3 | Begin review of live evaluations **RISK - have to make changes based on whatever feedback is in before end of pilot phase. May not have many global L1s to use. Can't go much beyond this date b/c no time to make changes/translate/input before launch | 2015-02-09 | 37 | 2015-03-11 | #REF! | Cara's team / Designers
March 9-13
3 | Changes from Beta Phase 3 by designers & send to translation as soon as pieces are ready (pay for priority) **RISK - translation not coming back in time if heavy re-working of material | 2015-03-11 | 28 | 2015-04-09 | #REF! | Designers
March 16-20
4 | Deadline for Phase 4 ENG content (for review) | 2015-03-16 | 1 | 2015-03-16 | #REF! | Designers
4 | Content review (Executive Advisor, regional manager) | 2015-03-17 | 4 | 2015-03-20 | #REF! | Cara liaises with reviewers
March 23-27
4 | Input changes from content review | 2015-03-23 | 5 | 2015-03-30 | #REF! | Cara liaises with reviewers / Designers
March 30 - April 3
4 | Final checking of English formatting before sending to translation | 2015-03-31 | 2 | 2015-04-02 | #REF! | Implementation team Graphic design required?? Is there a logo for the program?
4 | Content translation | 2015-04-03 | 14 | 2015-04-17 | #REF! | Tatiana / Designers to submit to her
April 6-10
4 | Facilitator prep | 2015-04-07 | 30 | 2015-05-08 | #REF! | Implementation team to coordinate with Facilitators How to coordinate with designers?
3 | Phase 3 content changes ready (send to translation) | 2015-04-09 | 1 | 2015-04-09 | #REF! | Tatiana
April 20-24
4 | Review French translation | 2015-04-20 | 5 | 2015-04-24 | #REF! | Designers have 48 hours
3 | Review translation as it comes back in | 2015-04-22 | 2 | 2015-04-23 | #REF! | Designers
3 | Edesigners input changes into Moodle (Whatever is ready first then pieces coming back from translation near deadline) | 2015-04-24 | 12 | 2015-05-06 | #REF! | Roger / John / Fred
April 27 - May 1
4 | Final checking of French formatting before printing | 2015-04-27 | 2 | 2015-04-28 | #REF! | Implementation team
4 | Print material for NCR and send docs to regions to print | 2015-04-29 | 7 | 2015-05-06 | #REF! | Implementation team
May 11-15
3 | PHASE 3 OFFICIAL LAUNCH | 2015-05-11 | 1 | 2015-05-11 | #REF! | Implementation team
4 | PHASE 4 PILOT | 2015-05-11 | 21 | 2015-05-29 | #REF! | Implementation team
June 1-5
4 | Designers review evaluations/observations & revise Phase 4 | 2015-06-01 | 18 | 2015-06-18 | #REF! | Designers
June 15-19
4 | Deadline for Phase 4 revisions | 2015-06-18 | 1 | 2015-06-18 | #REF! | Designers
4 | Content translation of changes | 2015-06-19 | 7 | 2015-06-26 | #REF! | Tatiana / Designers to submit to her
June 29 - July 3
4 | Facilitator prep | 2015-06-29 | 21 | 2015-07-17 | #REF! | Implementation team to coordinate with Facilitators How to coordinate with designers?
4 | Review French translation | 2015-06-29 | 3 | 2015-07-02 | #REF! | Designers have 48 hours
4 | Final checking of French formatting before printing | 2015-07-03 | 4 | 2015-07-07 | #REF! | Implementation team
July 6-10
4 | Print material for NCR and send docs to regions to print | 2015-07-08 | 7 | 2015-07-15 | #REF! | Implementation team
July 20-24
4 | PHASE 4 OFFICIAL LAUNCH | 2015-07-20 | 1 | 2015-07-20 | #REF! | Implementation team
Formulas:
Remaining days = NETWORKDAYS(#REF!,[End Date])
Remaining days = NETWORKDAYS(#REF!, [End Date])